## Product Backlog
SuperCrush
Sprint 1 | PoCT (4/4/2014)
Total Effort |  | 61.5 | 70.5
ID | Description | Estimated Effort | Actual Effort
1 | Player (Phase 1) | 6.5 | 7.75
2 | Hazards (Phase 1) | 5 | 6
3 | Environment (Phase 1) | 0.5 | 0.5
4 | Camera | 0.5 | 0.5
5 | Checkpoints (Phase 1) | 1 | 0.5
6 | Level 2 (Phase 1) | 3 | 0.5
7 | Level 4 (Phase 1) | 3 | 2.75
8 | Level 5 (Phase 1) | 1 | 1.5
9 | Documents | 22 | 20
10 | Miscellaneous | 19 | 30.5
Sprint 2 | PoCG (4/11/2014)
Total Effort |  | 56 | 62.5
ID | Description | Estimated Effort | Actual Effort
11 | Player (Phase 2) | 4 | 5.5
12 | Hazards (Phase 2) | 4 | 5
13 | Environment (Phase 2) | 4 | 4.5
14 | Pickup Comics | 4 | 1
15 | Checkpoints (Phase 2) | 1 | 0.5
16 | HUD | 2 | 2
17 | Level 1 (Phase 1) | 5 | 0.5
18 | Level 3 (Phase 1) | 5 | 3.5
19 | Cutscenes (Phase 1) | 3 | 3
20 | Documents | 3 | 5
21 | Miscellaneous | 21 | 32
Sprint 3 | VS (4/17/2014)
Total Effort |  | 55 | 60
ID | Description | Estimated Effort | Actual Effort
22 | NPCs | 3 | 1
23 | Background | 3 | 3.5
24 | Menus (Phase 1) | 11 | 5.5
25 | Cutscenes (Phase 2) | 3 | 7.5
26 | Level 1 (Phase 2) | 1 | 4
27 | Level 2 (Phase 2) | 1 | 1
28 | Level 3 (Phase 2) | 1 | 1.5
29 | Level 4 (Phase 2) | 3 | 3
30 | Level 5 (Phase 2) | 3 | 3.5
31 | Scoring | 2 | 1
32 | Checkpoints (Phase 3) | 2 | 1
33 | Special Effects | 3 | 3
34 | Miscellaneous | 19 | 24.5
Sprint 4 | Alpha (4/25/2014)
Total Effort |  | 59 | 66
ID | Description | Estimated Effort | Actual Effort
35 | Menus (Phase 2) | 12 | 11
36 | Tutorial (Phase 1) | 3 | 0.5
37 | Cutscenes (Phase 3) | 3 | 2
38 | Level 1 (Phase 3) | 2 | 2
39 | Level 2 (Phase 3) | 2 | 2
40 | Level 3 (Phase 3) | 3 | 2
41 | Level 4 (Phase 3) | 1 | 2
42 | Level 5 (Phase 3) | 3 | 2
43 | New Levels | 3 | 20.25
44 | Miscellaneous | 27 | 22.25
Sprint 5 | Beta (5/2/2014)
Total Effort |  | 48 | 60
ID | Description | Estimated Effort | Actual Effort
45 | Sounds | 1 | 5
46 | Art Assets | 3 | 17.5
47 | Level 1 (Phase 4) | 3 | 2.5
48 | Level 2 (Phase 4) | 3 | 2
49 | Level 3 (Phase 4) | 3 | 3
50 | Level 4 (Phase 4) | 3 | 3.5
51 | Level 5 (Phase 4) | 3 | 2.5
52 | Levels 6 and 7 (Phase 2) | 2 | 4.5
53 | Miscellaneous | 27 | 19.5
Sprint 6 | RTM (5/9/2014)
Total Effort |  | 46 | 58.5
ID | Description | Estimated Effort | Actual Effort
54 | Installer | 1 | 0.5
55 | Marketing Materials | 10 | 14.5
56 | Trailer | 6 | 5
57 | Documents | 2 | 26
58 | Miscellaneous | 27 | 12.5

## POCT
Proof of Concept Technology | [5 empty] | Days in Sprint
[6 empty] | 0 | 2014-03-29 | 2014-03-30 | 2014-03-31 | 2014-04-01 | 2014-04-02 | 2014-04-03 | 2014-04-04 |  | Production | Design | Art | Programming | Total Individual Hours
ID | Effort | Task | Department | Est. Effort | Name | 21.25 | 0 | 4 | 13 | 15 | 6 | 10.75 | 0.5 | Michael Crawford (MC) | 1 | 16 |  |  | 17
1 | 7.75 | Player (Phase 1) | [11 empty] | Amanda East (AE) | 1 |  | 16.5 |  | 17.5
| 0.5 | Player Shorthop | SD | 1 | TY |  | 2014-04-01: 0.5 | Matt Worrell (MW) | 3 | 14.5 |  |  | 17.5
| 0.5 | Player Death (simple version) | SD | 1 | TY |  | 2014-04-03: 0.5 | Trevor Youngblood (TAY) | 4 |  |  | 14.5 | 18.5
| 0.5 | Player Prefab finalization | SD | 0.5 | TY |  | 2014-04-02: 0.5 | Total Department Hours | 9 | 30.5 | 16.5 | 14.5 | 70.5
| 1 | Player Falling Sprite | Art | 0.5 | AE |  | 2014-04-02: 0.5; 2014-04-03: 0.5
| 0.5 | Update Player Sprint Animation | Art | 0.5 | AE | 0.5
| 1.5 | Player Run Animation Implementation | LD | 0.5 | MC/MW |  | 2014-04-01: 1; 2014-04-02: 0.5
| 0.25 | Player Sprint Animation Implementation | LD | 0.5 | MC/MW |  | 2014-04-02: 0.25
| 1 | Player Jump Animation Implementation | LD | 0.5 | MC/MW |  | 2014-04-02: 0.5; 2014-04-03: 0.5
| 0.5 | Player Idle Animation Implementation | LD | 0.5 | MC/MW |  | 2014-04-02: 0.5
| 1 | Player Fall Animation Implementation | LD | 0.5 | MW | bar: 2014-04-03
| 0.5 | Player Wall Cling Animation Implementation | LD | 0.5 | MC/MW |  | 2014-04-02: 0.25; 2014-04-03: 0.25
2 | 6 | Hazards (Phase 1) | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards
| 2 | Update Spike Animation | Art | 0.5 | AE |  | 2014-04-01: 2
| 0.5 | Resize Mine Animation | Art | 0.5 | AE |  | 2014-04-01: 0.5
| 0.5 | Mine Animation Implementation | LD | 0.5 | MC |  | 2014-04-03: 0.5
| 0.25 | Rocket Animation Implementation | LD | 0.5 | MC |  | 2014-04-03: 0.25
| 0.25 | Spike Animation Implementation | LD | 0.5 | MC |  | 2014-04-03: 0.25
| 0.5 | Rocket Launcher Script | SD | 1 | TY |  | 2014-04-04: 0.5
| 0.5 | Missile Script | SD | 1 | TY |  | 2014-04-03: 0.5
| 1.5 | Hazard Prefabs | SD | 0.5 | MW/MC/TY |  | 2014-04-01: 0.5; 2014-04-02: 0.5; 2014-04-03: 0.5
3 | 0.5 | Environment (Phase 1) | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles
| 0.5 | Environment Tile Prefabs | LD | 0.5 | MC |  | 2014-04-03: 0.5
4 | 0.5 | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera
| 0.5 | Camera Script | SD | 0.5 | TY |  | 2014-04-03: 0.5
5 | 0.5 | Checkpoints (Phase 1) | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints
| 0.5 | Checkpoint Collision Script | SD | 1 | TY |  | 2014-04-03: 0.5
6 | 0.5 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2
| 0.5 | Build Level 2 | LD | 3 | MW |  | 2014-04-02: 0.5
7 | 2.75 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4
| 2.75 | Build Level 4 | LD | 3 | MC | 0.75 | bar: 2014-03-31 to 2014-04-01
8 | 1.5 | Level 5 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4
| 1.5 | Level 5 concept | LD | 1 | MC | 1.5
9 | 20 | Documents | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation
| 6 | GDD Updates | Production | 3 | ALL | 2 | 2014-03-31: 4
| 5 | ADB Updates | Production | 8 | ALL |  | 2014-04-01: 3; 2014-04-03: 2
| 3 | ADB Draft | Production | 3 | AE | bar: 2014-03-30 to 2014-04-01
| 1 | Product Backlog Draft | Production | 1 | TY | 1
| 1 | ADP Updates | Production | 4 | TY | bar: 2014-04-01
| 4 | ADP Draft | Production | 3 | MW/TY | 2 | 2014-03-31: 2
10 | 30.5 | Miscellaneous | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation
| 1 | Create Color Pallette | Art | 1 | AE | 1
| 1 | File Icon Concept | Art | 1 | AE | bar: 2014-03-31
| 0.5 | Learn how to do animations in Unity | SD | 2 | TY |  | 2014-04-01: 0.5
| 8.5 | Debug Perforce Problems | SD | 1 | TY | 0.5 | 2014-03-30: 2; 2014-03-31: 3; 2014-04-01: 3
| 0.5 | Clean up project files | Production | 2 | TY |  | 2014-04-03: 0.5
| 1 | Individual Meetings | Production | 3 | ALL | bar: 2014-04-02
| 1 | Integration testing and Bug Fixing | Production | 1 | MC/TY | bar: 2014-04-03
| 13 | Perforce Integration | Production | 4 | ALL | 8 | bar: 2014-03-30 to 2014-04-03
| 4 | Product Backlog Updates | Production | 4 | ALL | 4

## POCG
Proof of Concept Gameplay | [5 empty] | Days in Sprint
[6 empty] | 0 | 2014-04-05 | 2014-04-06 | 2014-04-07 | 2014-04-08 | 2014-04-09 | 2014-04-10 | 2014-04-11 |  | Production | Design | Art | Programming | Total Individual Hours
ID | Effort | Task | Department | Est. Effort | Name | 6.5 | 0 | 0 | 11.5 | 9.5 | 15.5 | 19.5 | 0 | Michael Crawford (MC) | 1 | 14 |  |  | 15
11 | 5.5 | Player (Phase 2) | [11 empty] | Amanda East (AE) | 1 |  | 14.5 |  | 15.5
| 3 | Player Animation Polish | Art | 1 | AE |  | 2014-04-08: 3 | Matt Worrell (MW) | 2 | 13 |  |  | 15
| 1 | Player Death Script (refined) | SD | 1 | TY | 1 | [7 empty] | Trevor Youngblood (TAY) | 1 |  |  | 16 | 17
| 0.5 | Victory Script | SD | 1 | TY |  | 2014-04-08: 0.5 | Total Department Hours | 5 | 27 | 14.5 | 16 | 62.5
| 1 | Player Sounds | SD | 1 | TY | bar: 2014-04-10
12 | 5 | Hazards (Phase 2)
| 2.5 | Spike Platform Animation | Art | 1 | AE |  | 2014-04-07: 2.5
| 1 | Moving Spike Script | SD | 1 | TY | bar: 2014-04-09
| 0.5 | Spike Platform Script | SD | 1 | TY |  | 2014-04-09: 0.5
| 1 | Hazard Sounds | SD | 1 | TY | bar: 2014-04-10
13 | 4.5 | Environment (Phase 2)
| 2.5 | Metal Boxes Sprite | Art | 1 | AE | 2.5
| 0.5 | Implement Grass Animation | LD | 1 | MC |  | 2014-04-07: 0.5
| 1.5 | Moving Grass Script | SD | 2 | TY |  | 2014-04-08: 1.5
14 | 1 | Pickup Comics
| 0.5 | Polish Pickup Animation | Art | 3 | AE |  | 2014-04-10: 0.5
| 0.5 | Pickup Script | SD | 1 | TY |  | 2014-04-08: 0.5
15 | 0.5 | Checkpoints (Phase 2)
| 0.5 | Polish Checkpoint Animation | Art | 1 | AE |  | 2014-04-10: 0.5
16 | 2 | HUD
| 0.5 | Find HUD Font | Art | 0.5 | AE |  | 2014-04-07: 0.5
| 0.5 | Pickup HUD Script | SD | 1 | TY |  | 2014-04-08: 0.5
| 1 | Timer Script | SD | 0.5 | TY | bar: 2014-04-08
17 | 0.5 | Level 1 (Phase 1)
| 0.5 | Level 1 Build | LD | 3 | MW |  | 2014-04-10: 0.5
| 0 | Polish Level 1 | LD | 2 | -
18 | 3.5 | Level 3 (Phase 1)
| 3 | Level 3 Build | LD | 3 | MC |  | 2014-04-07: 3
| 0.5 | Polish Level 3 | LD | 2 | MC |  | 2014-04-07: 0.5
19 | 3 | Cutscenes (Phase 1)
| 3 | Cutscene Concept Art | Art | 3 | AE |  | 2014-04-09: 3
20 | 5 | Documents
| 2 | GDD Updates | Production | 1 | ALL | 2
| 1 | ADP Updates | Production | 1 | TY | 1
| 2 | Sprint Retrospective | Production | 1 | MW |  | 2014-04-07: 2
21 | 32 | Miscellaneous
| 3 | General Art Polish | Art | 3 | AE |  | 2014-04-10: 3
| 8 | General Code Polish | SD | 3 | TY |  | 2014-04-08: 1; 2014-04-09: 4; 2014-04-10: 3
| 9.5 | Playtesting | Production | 4 | ALL |  | 2014-04-07: 2.5; 2014-04-09: 3; 2014-04-10: 4
| 8 | Integration Testing and Bug Fixing | Production | 6 | ALL |  | 2014-04-09: 4; 2014-04-10: 4
| 2 | Find Sounds | Production | 2 | MW |  | 2014-04-10: 2
| 1.5 | Individual Meetings | Production | 3 | ALL |  | 2014-04-08: 1.5

## VS
Vertical Slice | [5 empty] | Days in Sprint
[6 empty] | 0 | 2014-04-11 | 2014-04-12 | 2014-04-13 | 2014-04-14 | 2014-04-15 | 2014-04-16 | 2014-04-17 |  | Production | Design | Art | Programming | Total Individual Hours
ID | Effort | Task | Department | Est. Effort | Name | 1 | 1 | 0 | 0 | 15 | 17.5 | 25.5 | 0 | Michael Crawford (MC) | 1 | 14 |  |  | 15
22 | 1 | NPCs | [11 empty] | Amanda East (AE) | 1 |  | 15 |  | 16
| 0.5 | Doctor Shocker Script | SD | 1 | TY |  | 2014-04-16: 0.5 | Matt Worrell (MW) | 2.5 | 9.5 |  |  | 12
| 0.5 | Crush Script | SD | 2 | TY |  | 2014-04-16: 0.5 | Trevor Youngblood (TAY) | 1 |  |  | 16 | 17
23 | 3.5 | Background | [11 empty] | Total Department Hours | 5.5 | 23.5 | 15 | 16 | 60
| 0.5 | Background Parallax Script | SD | 2 | TY |  | 2014-04-16: 0.5
| 3 | Background Music | SD | 1 | MW/TY | bar: 2014-04-14 to 2014-04-16
24 | 5.5 | Menus (Phase 1)
| 0.5 | Pause Menu Art | Art | 3 | AE |  | 2014-04-15: 0.5
| 1.5 | Options Menu Art | Art | 3 | AE |  | 2014-04-15: 1.5
| 1.5 | Pause Menu Script | SD | 3 | TY |  | 2014-04-16: 1.5
| 2 | Options Menu Script | SD | 2 | TY |  | 2014-04-16: 2
25 | 7.5 | Cutscenes (Phase 2)
| 7.5 | Cutscene Art | Art | 3 | AE | 1 | 2014-04-14: 6.5
26 | 4 | Level 1 (Phase 2)
| 4 | Polish Level 1 | LD | 1 | MC/MW |  | 2014-04-14: 2; 2014-04-16: 2
27 | 1 | Level 2 (Phase 2)
| 1 | Polish Level 2 | LD | 1 | MC | bar: 2014-04-15
28 | 1.5 | Level 3 (Phase 2)
| 1.5 | Polish Level 3 | LD | 1 | MC |  | 2014-04-14: 1; 2014-04-15: 0.5
29 | 3 | Level 4 (Phase 2)
| 3 | Complete Level 4 | LD | 3 | MW |  | 2014-04-15: 1; 2014-04-16: 2
30 | 3.5 | Level 5 (Phase 2)
| 3.5 | Build Level 5 | LD | 3 | MC |  | 2014-04-11: 1; 2014-04-14: 2; 2014-04-16: 0.5
31 | 1 | Scoring
| 1 | Scoring Script | SD | 2 | TY | bar: 2014-04-16
32 | 1 | Checkpoints (Phase 3)
| 1 | Checkpoint Popup Animation | SD | 2 | TY | bar: 2014-04-15
33 | 3 | Special Effects
| 1 | Scene Fade-in/out | SD | 1 | TY | bar: 2014-04-15
| 1 | GUI Text Outline | SD | 1 | TY | bar: 2014-04-16
| 1 | Particle Effects | SD | 1 | TY | bar: 2014-04-16
34 | 24.5 | Miscellaneous
| 5 | Polish Art | Art | 3 | AE |  | 2014-04-15: 2; 2014-04-16: 3
| 6 | Polish Scripts | SD | 3 | TY |  | 2014-04-15: 3; 2014-04-16: 3
| 7 | Playtesting | Production | 4 | MC/MW |  | 2014-04-15: 3; 2014-04-16: 4
| 5 | Integration Testing and Bug Fixing | Production | 6 | TY |  | 2014-04-14: 1; 2014-04-15: 2; 2014-04-16: 2
| 1.5 | Individual Meetings | Production | 3 | ALL |  | 2014-04-14: 1.5

## Alpha
Alpha | [5 empty] | Days in Sprint
[6 empty] | 0 | 2014-04-19 | 2014-04-20 | 2014-04-21 | 2014-04-22 | 2014-04-23 | 2014-04-24 | 2014-04-25 |  | Production | Design | Art | Programming | Total Individual Hours
ID | Effort | Task | Department | Est. Effort | Name | 5 | 0 | 2 | 11.25 | 16 | 19 | 12.75 | 0 | Michael Crawford (MC) | 1 | 14 |  |  | 15
35 | 11 | Menus (Phase 2) | [11 empty] | Amanda East (AE) | 1 |  | 16 |  | 17
| 4 | Main Menu Art | Art | 3 | AE |  | 2014-04-21: 1.5; 2014-04-22: 1.5; 2014-04-24: 1 | Matt Worrell (MW) | 2 | 14 |  |  | 16
| 1.5 | Level Select Art | Art | 3 | AE |  | 2014-04-22: 1.5 | Trevor Youngblood (TAY) | 1.5 |  |  | 16.5 | 18
| 3.5 | All Menu Scripts | SD | 3 | TY |  | 2014-04-21: 2; 2014-04-22: 1.5 | Total Department Hours | 5.5 | 28 | 16 | 16.5 | 66
| 2 | Gameplay Menus | SD | 3 | TY |  | 2014-04-21: 1.5; 2014-04-22: 0.5
36 | 0.5 | Tutorial (Phase 1) | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards
| 0.5 | Tutorial Art | Art | 3 | AE |  | 2014-04-23: 0.5
37 | 2 | Cutscenes (Phase 3) | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles
| 2 | Cutscene Camera Script | SD | 3 | TY |  | 2014-04-23: 2
38 | 2 | Level 1 (Phase 3) | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera
| 2 | Refine Level 1 | LD | 2 | MC |  | 2014-04-21: 0.5; 2014-04-22: 0.5; 2014-04-23: 1
39 | 2 | Level 2 (Phase 3) | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints
| 2 | Refine Level 2 | LD | 2 | MC | bar: 2014-04-22 to 2014-04-23
40 | 2 | Level 3 (Phase 3) | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2 | Level 2
| 2 | Refine Level 3 | LD | 3 | MC | bar: 2014-04-22 to 2014-04-23
41 | 2 | Level 4 (Phase 3) | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4
| 2 | Refine Level 4 | LD | 1 | MC | bar: 2014-04-22 to 2014-04-23
42 | 2 | Level 5 (Phase 3) | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4
| 2 | Refine Level 5 | LD | 3 | MC | bar: 2014-04-22 to 2014-04-23
43 | 20.25 | New Levels | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation
| 6.5 | New Level Concepts | LD | 1 | ALL | 5 | 2014-04-21: 1.5
| 7 | Level 6 | LD | 1 | MW |  | 2014-04-21: 4; 2014-04-22: 3
| 6.75 | Level 7 | LD | 1 | MC |  | 2014-04-22: 1.5; 2014-04-23: 4.5; 2014-04-24: 0.75
44 | 22.25 | Miscellaneous | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation
| 8.75 | Finalize Art | Art | 3 | AE |  |  | 2 | 0.25 | 0.5 | 4 | 2
| 3 | Finalize Scripts | SD | 3 | TY |  | 2014-04-24: 3
| 4 | Playtesting | Production | 12 | ALL |  | 2014-04-23: 1; 2014-04-24: 3
| 5 | Integration testing and Bug Fixing | Production | 6 | ALL |  | 2014-04-23: 2; 2014-04-24: 3
| 1.5 | Individual Meetings | Production | 3 | ALL |  | 2014-04-22: 1.5

## Beta
Beta | [5 empty] | Days in Sprint
[6 empty] | 0 | 2014-04-26 | 2014-04-27 | 2014-04-28 | 2014-04-29 | 2014-04-30 | 2014-05-01 | 2014-05-02 |  | Production | Design | Art | Programming | Total Individual Hours
ID | Effort | Task | Department | Est. Effort | Name | 1 | 0 | 0 | 8.5 | 16.5 | 20 | 14 | 0 | Michael Crawford (MC) | 1 | 12 |  |  | 13
45 | 5 | HUD | [11 empty] | Amanda East (AE) | 1 |  | 15 |  | 16
| 5 | Final HUD Tweaks | LD | 1 | TY |  | 2014-04-28: 1; 2014-04-29: 3; 2014-05-01: 1 | Matt Worrell (MW) | 2.5 | 10 |  |  | 12.5
46 | 17.5 | Art Assets | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Trevor Youngblood (TAY) | 2.5 |  |  | 16 | 18.5
| 17.5 | Polish Assets | Art | 3 | AE |  | 2014-04-28: 7; 2014-04-29: 2; 2014-04-30: 6; 2014-05-01: 2.5 | Total Department Hours | 7 | 22 | 15 | 16 | 60
47 | 2.5 | Level 1 (Phase 4) | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles | Environment Tiles
| 2.5 | Polish Level 1 | LD | 3 | ALL |  | 2014-04-28: 0.5; 2014-04-30: 1; 2014-05-01: 1
48 | 2 | Level 2 (Phase 4) | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera | Camera
| 2 | Polish Level 2 | LD | 3 | ALL | bar: 2014-04-30 to 2014-05-01
49 | 3 | Level 3 (Phase 4) | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints | Checkpoints
| 3 | Polish Level 3 | LD | 3 | ALL |  | 2014-04-30: 2; 2014-05-01: 1
50 | 3.5 | Level 4 (Phase 4) | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4
| 3.5 | Polish Level 4 | LD | 3 | ALL | 1 | 2014-04-30: 1.5; 2014-05-01: 1
51 | 2.5 | Level 5 (Phase 4) | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4
| 2.5 | Polish Level 5 | LD | 3 | ALL |  | 2014-04-30: 1.5; 2014-05-01: 1
52 | 4.5 | Levels 6 and 7 (Phase 2) | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation
| 2.25 | Level 6 | LD | 1 | ALL |  | 2014-04-29: 1; 2014-04-30: 0.5; 2014-05-01: 0.75
| 2.25 | Level 7 | LD | 1 | ALL |  | 2014-04-29: 1; 2014-04-30: 0.5; 2014-05-01: 0.75
53 | 19.5 | Miscellaneous | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation
| 11 | Playtesting | Production | 12 | ALL |  | 2014-04-29: 8; 2014-04-30: 3
| 7 | Integration testing and Bug Fixing | Production | 12 | ALL |  | 2014-04-30: 3; 2014-05-01: 4
| 1.5 | Individual Meetings | Production | 3 | ALL |  | 2014-04-29: 1.5

## RTM
Release to Manufacturer | [5 empty] | Days in Sprint
[6 empty] | 0 | 2014-05-03 | 2014-05-04 | 2014-05-05 | 2014-05-06 | 2014-05-07 | 2014-05-08 | 2014-05-09 |  | Production | Design | Art | Programming | Total Individual Hours
ID | Effort | Task | Department | Est. Effort | Name | 0 | 0 | 0 | 13 | 13.5 | 8.5 | 23 | 0.5 | Michael Crawford (MC) | 13 |  |  |  | 13
54 | 0.5 | Installer | [11 empty] | Amanda East (AE) | 1.5 |  | 14 |  | 15.5
| 0.5 | Build Installer | SD | 1 | TY |  | 2014-05-08: 0.5 | Matt Worrell (MW) | 11 | 4 |  |  | 15
55 | 14.5 | Marketing Materials | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Hazards | Trevor Youngblood (TAY) | 13 | 1 |  | 1 | 15
| 0.5 | Archive Discs | SD | 1 | TY |  | 2014-05-08: 0.5 | Total Department Hours | 38.5 | 5 | 14 | 1 | 58.5
| 5 | Poster | Art | 3 | AE |  | 2014-05-05: 5
| 6 | DVD Case Art | Art | 3 | AE |  | 2014-05-08: 5.5; 2014-05-09: 0.5
| 3 | DVD Disc Art | Art | 3 | AE |  | 2014-05-06: 3
56 | 5 | Trailer | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4 | Level 4
| 1 | Capture Game Footage for Trailer | LD | 3 | TY | bar: 2014-05-06
| 4 | Make Trailer | LD | 3 | MW |  | 2014-05-08: 4
57 | 26 | Documents | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation
| 19 | GDD Updates | Production | 1 | ALL |  | 2014-05-05: 5; 2014-05-06: 4; 2014-05-07: 2.5; 2014-05-08: 7.5
| 7 | Other Document Updates | Production | 1 | ALL |  | 2014-05-06: 4; 2014-05-08: 3
58 | 12.5 | Miscellaneous | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation | Documentation
| 4 | Playtesting | Production | 12 | ALL |  | 2014-05-05: 1; 2014-05-07: 2; 2014-05-08: 1
| 7 | Integration testing and Bug Fixing | Production | 12 | ALL |  | 2014-05-05: 2; 2014-05-07: 4; 2014-05-08: 1
| 1.5 | Individual Meetings | Production | 3 | ALL |  | 2014-05-06: 1.5